## Tool
Stakeholder Engagement Map
Program / Project: | Copilot for Microsoft 365 Implementation
Date: | 2024-03-05 |  | Eyes Only: Private Content for Enablement Team
Stakeholder Engagement Lead: | <name>
5=High 1=Low
Stakeholder | Fulfill Expectations | Manage Closely | Keep Informed | Monitor | Level of Interest | Level of Influence | Influence Score | Resistance Level | Overall Alignment | Have they been interviewed? | If interviewed, when? | Relationship Owner (vTeam member) | Role | Primary Alignment Method | Notes
Exec Sponsor | Yes | Yes |  |  | 5 | 5 | 10 | 0 | 4 | Yes | <insert date> |  |  | Bi-weekly 1:1
Success Owner | Yes | Yes |  |  | 4 | 4 | 8 | 2 | 4 | Yes | <insert date> |  |  | Status Report
Unit Leader 1 | Yes | Yes |  |  | 4 | 4 | 8 | 2 | 4 | Yes | <insert date> |  |  | Internal News Updates
Unit Leader 2 | Yes | No |  |  | 4 |  | 4 | 4 | 3 | No | <insert date> |  |  | Project Plan
Unit Leader 3 | No | No |  |  | 3 | 3 | 6 | 3 |  | No | <insert date>
IT Leader | Yes | Yes |  |  |  |  | 0 | 2 | 4 | Yes | <insert date> |  |  | Status Reports & Service Health Reviews
Technical Readiness Lead | Yes | Yes |  |  | 5 | 3 | 8 | 1 | 4 | Yes | <insert date> |  |  | Bi-weekly Stand Up
Operations Lead | No | No | Yes |  | 2 | 3 | 5 | 3 | 1 | No | <insert date>
M365 Tenant Admin | No | Yes | Yes |  | 3 | 3 | 6 | 3 | 2 | No | <insert date> |  |  | Bi-weekly Stand Up

## Stakeholder Chart
Data
Stakeholder | Interest | Sum of Influence
IT Leader |  | 0
(empty)
Unit Leader 2 | 4 | 4
Operations Lead | 2 | 5
M365 Tenant Admin | 3 | 6
Unit Leader 3 | 3 | 6
Success Owner | 4 | 8
Technical Readiness Lead | 5 | 8
Unit Leader 1 | 4 | 8
Exec Sponsor | 5 | 10
Total Result | 30 | 55

## Lookups (hidden)
Yes | 1 | 0
No | 2 | 1
| 3 | 2
| 4 | 3
| 5 | 4
5